## Start here
Project Costing & Profitability
Axcell Financial Consulting
Budget vs actual, % complete, forecast at completion and gross vs net profit
How to use it (about 10 minutes)
Step 1 | Fill 'Your settings' below: company name, currency, the report date (costs after this date are ignored), your overhead rate and the forecast method.
Step 2 | On 'Projects', enter each project once: contract value, approved variations, budget by cost category and dates. Each month, update % complete and invoiced to date.
Step 3 | Record labour on 'Labour' (date, project, role, hours). Set up the hourly cost of each role in the rate card on the right of that sheet.
Step 4 | Record materials, subcontractor and other direct costs on 'Other costs' (date, project, category, amount), e.g. from supplier invoices.
Step 5 | Read 'Portfolio' for all projects at once, then pick one project on 'Project detail' to see budget vs actual by category, the forecast and gross vs net profit.
Colour legend
1,250 | Input: blue text on light-yellow. Type your own numbers here.
1,250 | Formula: black text. Calculated for you, do not overwrite.
(1,250) | Brackets mean a negative number (a loss, an outflow or a shortfall).
Earned value | Budget × % complete: what the work done so far should have cost. Compare it with actual cost to see if you are over or under budget.
(12,500) | Red / brackets on variance columns = over budget, or a forecast loss.
Your settings
Company name | Example Contracting Co. | Shown on the Portfolio and Project detail sheets.
Currency | Your currency | Type your currency code, e.g. SAR, AED, EGP, USD. Labels only; no conversion.
Report date | 2026-10-31 | Costs dated after this date are not counted. Usually the last day of the month you are reviewing.
Overhead rate (% of direct cost) | 12% | Your company overheads (office, management, admin) as a % of direct project cost. Example only: work out your own from last year's accounts.
Forecast method | Current cost performance | 'Current cost performance': remaining work costs what it has cost so far (safer if you are over budget). 'Remaining work at budget': remaining work costs exactly the budget.
Margin fade alert (points) | 2% | Flag a project when the forecast gross margin is this much below the budget margin (2% = two percentage points).
Good to know
• Gross profit = contract value − direct project costs (labour, materials, subcontractors, other). Net profit = gross profit − overhead at your overhead rate. A project can make a gross profit and still lose money after overheads.
• % complete is your honest estimate of physical progress (work done ÷ total work), not the share of budget spent. Spending 60% of the budget at 40% complete is a warning, not progress.
• Estimate at completion (EAC) = actual cost to date + forecast cost to complete. If your project manager has a better estimate, type it in 'Your estimate to complete' on Projects: it overrides the formula.
• Hourly cost rate = monthly cost of the person (salary, allowances, benefits) ÷ productive hours per month. The rates in this file are examples, not market data.
• Use it after the go/no-go decision: Axcell's Big Contract Deal Sheet helps decide whether to take a contract; this tracker follows its delivery.
Illustrative tool for decision support, not financial, tax or legal advice. The example figures are made up for illustration.
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact

## Portfolio
Portfolio: all projects at a glance
Axcell Financial Consulting · Project Costing & Profitability
Example Contracting Co. · Costs to 31 Oct 2026 · Amounts in Your currency · Overhead 12.0% of direct cost · Forecast: Current cost performance
A. PROFITABILITY AND FORECAST BY PROJECT
ID | Project | Status | Contract value (incl. variations) | Budget cost | Budget gross margin % | % complete | Actual cost to date | Earned value (budget × % complete) | Cost variance (+ under / − over) | Cost perform. (earned ÷ actual) | Forecast cost to complete | Estimate at completion (EAC) | Forecast vs budget (+ under / − over) | Forecast gross profit | Forecast gross margin % | Margin fade (points) | Overhead | Forecast net profit | Forecast net margin % | Billed ahead / (behind) | Late by (days) | What to look at
P01 | Example: Office fit-out, Building A | In progress | 1260000 | 900000 | 28.57% | 70% | 680300 | 630000 | -50300 | 0.92606 | 291557.1429 | 971857.1429 | -71857.1429 | 288142.8571 | 22.87% | -5.703% | 116622.8571 | 171520 | 13.61% | -62000 | 36 | Forecast over budget
P02 | Example: Warehouse racking installation | In progress | 480000 | 355000 | 26.04% | 40% | 135060 | 142000 | 6940 | 1.0514 | 202590 | 337650 | 17350 | 142350 | 29.66% | 3.615% | 40518 | 101832 | 21.21% | 8000 | 0 | On track
P03 | Example: Clinic MEP upgrade | Completed | 300000 | 220000 | 26.67% | 100% | 236270 | 220000 | -16270 | 0.93114 | 0 | 236270 | -16270 | 63730 | 21.24% | -5.423% | 28352.4 | 35377.6 | 11.79% | 0 | 14 | Forecast over budget
P04 | Example: Retail store refurbishment | In progress | 650000 | 515000 | 20.77% | 25% | 159990 | 128750 | -31240 | 0.80474 | 479970 | 639960 | -124960 | 10040 | 1.545% | -19.22% | 76795.2 | -66755.2 | -10.27% | -12500 | 31 | Forecast loss after overhead
P05 | Example: Showroom lighting upgrade | Not started | 150000 | 105000 | 30% | 0% | 0 | 0 | 0 |  | 105000 | 105000 | 0 | 45000 | 30% | 0% | 12600 | 32400 | 21.6% | 0 | 0 | Not started
| Total portfolio |  | 2840000 | 2095000 | 26.23% | 53.5% | 1211620 | 1120750 | -90870 | 0.925 | 1079117.1429 | 2290737.1429 | -195737.1429 | 549262.8571 | 19.34% | -6.892% | 274888.4571 | 274374.4 | 9.661% | -66500 |  | 3 flagged: forecast loss or overrun
Gross profit = contract value − direct costs. Net profit = gross profit − overhead (overhead rate × direct cost). Cost performance below 1.00 means each unit of work is costing more than budgeted.
Billed ahead / (behind) = invoiced to date − contract value × % complete. Behind means work done but not yet invoiced: a cash risk.
B. BUDGET VS ACTUAL TO DATE BY COST CATEGORY
ID | Project | Labour budget | Labour actual | Materials budget | Materials actual | Subcontractors budget | Subcontractors actual | Other budget | Other actual | Total budget | Total actual | % of budget used | % complete
P01 | Example: Office fit-out, Building A | 260000 | 205300 | 420000 | 300000 | 180000 | 150000 | 40000 | 25000 | 900000 | 680300 | 75.59% | 70%
P02 | Example: Warehouse racking installation | 90000 | 32060 | 210000 | 88000 | 40000 | 10000 | 15000 | 5000 | 355000 | 135060 | 38.05% | 40%
P03 | Example: Clinic MEP upgrade | 140000 | 158270 | 40000 | 41000 | 30000 | 30000 | 10000 | 7000 | 220000 | 236270 | 107.4% | 100%
P04 | Example: Retail store refurbishment | 150000 | 51990 | 230000 | 70000 | 110000 | 33000 | 25000 | 5000 | 515000 | 159990 | 31.07% | 25%
P05 | Example: Showroom lighting upgrade | 40000 | 0 | 50000 | 0 | 10000 | 0 | 5000 | 0 | 105000 | 0 | 0% | 0%
| Total portfolio | 680000 | 447620 | 950000 | 499000 | 370000 | 223000 | 95000 | 42000 | 2095000 | 1211620 | 57.83% | 53.5%
Actual in red = that category has used more than (% complete + 5 points) of its budget: it is spending faster than the work is progressing.
C. DATA CHECKS (should all be 0)
| Labour rows with hours but a project ID not on the Projects sheet | [5 empty] | 0
| Labour rows with hours but no rate (role not on the rate card and no override) | [5 empty] | 0
| Cost rows with an amount but a project ID not on the Projects sheet | [5 empty] | 0
| Cost rows with an amount but no valid category | [5 empty] | 0
| Rows with an amount or hours but no date (not counted) | [5 empty] | 0
| Rows dated after the report date (not counted yet) | [5 empty] | 0
| Duplicate project IDs on the Projects sheet | [5 empty] | 0
Illustrative tool for decision support, not financial advice. Example figures are made up.
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact

## Project detail
Project detail: budget vs actual and forecast
Axcell Financial Consulting · Project Costing & Profitability
Example Contracting Co. · Costs to 31 Oct 2026 · Amounts in Your currency
row
Choose project ID | P04 | Example: Retail store refurbishment · Example Client 4 | [6 empty] | 4
Status | In progress |  | Planned end |  | 2027-02-28
% complete | 25% |  | Forecast end |  | 2027-03-31
Contract value (incl. variations) | 650000 |  | Schedule slip (days) |  | 31
Start date | 2026-08-15 |  | What to look at |  | Forecast loss after overhead
A. DIRECT COSTS BY CATEGORY
Cost category | Budget | Earned budget (budget × % complete) | Actual to date | Variance to date (+ under / − over) | % of budget used | Forecast cost to complete | Estimate at completion (EAC) | Forecast vs budget (+ under / − over)
Labour | 150000 | 37500 | 51990 | -14490 | 34.66% | 139797.0874 | 191787.0874 | -41787.0874
Materials | 230000 | 57500 | 70000 | -12500 | 30.43% | 214355.534 | 284355.534 | -54355.534
Subcontractors | 110000 | 27500 | 33000 | -5500 | 30% | 102517.8641 | 135517.8641 | -25517.8641
Other | 25000 | 6250 | 5000 | 1250 | 20% | 23299.5146 | 28299.5146 | -3299.5146
Total direct cost | 515000 | 128750 | 159990 | -31240 | 31.07% | 479970 | 639960 | -124960
Check: EAC here = EAC on Portfolio | [6 empty] | OK
Labour hours logged to date: 1,023 · Average labour cost per hour: 50.82
Forecast method: Current cost performance. Cost to complete is spread across categories in proportion to their remaining budget.
B. GROSS VS NET PROFIT
| Budget | Earned to date | Forecast at completion
Contract value / revenue | 650000 | 162500 | 650000 |  | • Gross profit shows whether the contract price covers the direct cost of doing the job.
Direct costs | 515000 | 159990 | 639960 |  | • Net profit also charges the project its share of company overheads (office, management, admin, insurance) at your overhead rate.
Gross profit | 135000 | 2510 | 10040 |  | • A project with a small gross profit can still lose money after overheads: watch both lines.
Gross margin % | 20.77% | 1.545% | 1.545% |  | • 'Earned to date' = revenue earned on the work done (contract × % complete) less actual cost so far.
Overhead (overhead rate × direct costs) | 61800 | 19198.8 | 76795.2
Net profit (after overhead) | 73200 | -16688.8 | -66755.2
Net margin % | 11.26% | -10.27% | -10.27%
Illustrative tool for decision support, not financial advice. Example figures are made up.
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact

## Projects
Projects: contract, budget and progress
Axcell Financial Consulting · Project Costing & Profitability
Amounts in Your currency. Enter costs as positive numbers. Update % complete and invoiced to date every month.
One row per project or contract (up to 10)
ID | Project name | Client | Status | Start date | Planned end | Forecast end | Original contract value | Approved variations | Budget: labour | Budget: materials | Budget: subcontractors | Budget: other | Total budget cost | % complete | Invoiced to date | Your estimate to complete (optional) | Notes
P01 | Example: Office fit-out, Building A | Example Client 1 | In progress | 2026-06-01 | 2026-12-15 | 2027-01-20 | 1200000 | 60000 | 260000 | 420000 | 180000 | 40000 | 900000 | 70% | 820000
P02 | Example: Warehouse racking installation | Example Client 2 | In progress | 2026-09-01 | 2026-12-31 | 2026-12-31 | 480000 | 0 | 90000 | 210000 | 40000 | 15000 | 355000 | 40% | 200000
P03 | Example: Clinic MEP upgrade | Example Client 3 | Completed | 2026-01-10 | 2026-06-30 | 2026-07-14 | 300000 | 0 | 140000 | 40000 | 30000 | 10000 | 220000 | 100% | 300000
P04 | Example: Retail store refurbishment | Example Client 4 | In progress | 2026-08-15 | 2027-02-28 | 2027-03-31 | 650000 | 0 | 150000 | 230000 | 110000 | 25000 | 515000 | 25% | 150000
P05 | Example: Showroom lighting upgrade | Example Client 5 | Not started | 2026-12-01 | 2027-03-31 | 2027-03-31 | 150000 | 0 | 40000 | 50000 | 10000 | 5000 | 105000 | 0% | 0
P06 | [12 empty] | 0
P07 | [12 empty] | 0
P08 | [12 empty] | 0
P09 | [12 empty] | 0
P10 | [12 empty] | 0
| Total | [5 empty] | 2780000 | 60000 | 680000 | 950000 | 370000 | 95000 | 2095000 |  | 1470000
Project IDs are used on the Labour and Other costs sheets: keep them short and unique (you can rename P01, P02 ...). Leave 'Your estimate to complete' blank to let the sheet forecast it.
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact

## Labour
Labour: hours × hourly cost rate
Axcell Financial Consulting · Project Costing & Profitability
Amounts in Your currency. One row per person/role per period (day, week or month). Pick the project ID and role from the lists.
Total labour logged |  |  | Hours: | 8808 |  | Cost: | 447620
Labour log | [7 empty] | Rate card (cost to the company, not selling price)
Date (or period end) | Project ID | Role (from rate card) | Person / description (optional) | Hours | Rate override (optional) | Hourly cost rate used | Labour cost | Role | Monthly cost per person | Productive hours per month | Hourly cost rate
2026-01-31 | P03 | Example: Project manager |  | 18 |  | 150 | 2700 | Example: Project manager | 24000 | 160 | 150
2026-01-31 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220 | Example: Site supervisor | 14400 | 160 | 90
2026-01-31 | P03 | Example: Technician |  | 181 |  | 50 | 9050 | Example: Technician | 8000 | 160 | 50
2026-01-31 | P03 | Example: Labourer |  | 188 |  | 30 | 5640 | Example: Labourer | 4800 | 160 | 30
2026-02-28 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-02-28 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-02-28 | P03 | Example: Technician |  | 181 |  | 50 | 9050
2026-02-28 | P03 | Example: Labourer |  | 188 |  | 30 | 5640
2026-03-31 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-03-31 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-03-31 | P03 | Example: Technician |  | 181 |  | 50 | 9050 | Monthly cost = salary + allowances + benefits + other employment costs. Example values only.
2026-03-31 | P03 | Example: Labourer |  | 188 |  | 30 | 5640 | Productive hours = hours actually available for project work (after leave, training, idle time).
2026-04-30 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-04-30 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-04-30 | P03 | Example: Technician |  | 181 |  | 50 | 9050
2026-04-30 | P03 | Example: Labourer |  | 188 |  | 30 | 5640
2026-05-31 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-05-31 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-05-31 | P03 | Example: Technician |  | 181 |  | 50 | 9050
2026-05-31 | P03 | Example: Labourer |  | 188 |  | 30 | 5640
2026-06-30 | P01 | Example: Project manager |  | 33 |  | 150 | 4950
2026-06-30 | P01 | Example: Site supervisor |  | 105 |  | 90 | 9450
2026-06-30 | P01 | Example: Technician |  | 328 |  | 50 | 16400
2026-06-30 | P01 | Example: Labourer |  | 342 |  | 30 | 10260
2026-06-30 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-06-30 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-06-30 | P03 | Example: Technician |  | 181 |  | 50 | 9050
2026-06-30 | P03 | Example: Labourer |  | 188 |  | 30 | 5640
2026-07-31 | P01 | Example: Project manager |  | 33 |  | 150 | 4950
2026-07-31 | P01 | Example: Site supervisor |  | 105 |  | 90 | 9450
2026-07-31 | P01 | Example: Technician |  | 328 |  | 50 | 16400
2026-07-31 | P01 | Example: Labourer |  | 342 |  | 30 | 10260
2026-07-31 | P03 | Example: Project manager |  | 18 |  | 150 | 2700
2026-07-31 | P03 | Example: Site supervisor |  | 58 |  | 90 | 5220
2026-07-31 | P03 | Example: Technician |  | 181 |  | 50 | 9050
2026-07-31 | P03 | Example: Labourer |  | 188 |  | 30 | 5640
2026-08-31 | P01 | Example: Project manager |  | 33 |  | 150 | 4950
2026-08-31 | P01 | Example: Site supervisor |  | 105 |  | 90 | 9450
2026-08-31 | P01 | Example: Technician |  | 328 |  | 50 | 16400
2026-08-31 | P01 | Example: Labourer |  | 342 |  | 30 | 10260
2026-08-31 | P04 | Example: Project manager |  | 14 |  | 150 | 2100
2026-08-31 | P04 | Example: Site supervisor |  | 44 |  | 90 | 3960
2026-08-31 | P04 | Example: Technician |  | 139 |  | 50 | 6950
2026-08-31 | P04 | Example: Labourer |  | 144 |  | 30 | 4320
2026-09-30 | P01 | Example: Project manager |  | 33 |  | 150 | 4950
2026-09-30 | P01 | Example: Site supervisor |  | 105 |  | 90 | 9450
2026-09-30 | P01 | Example: Technician |  | 328 |  | 50 | 16400
2026-09-30 | P01 | Example: Labourer |  | 342 |  | 30 | 10260
2026-09-30 | P02 | Example: Project manager |  | 13 |  | 150 | 1950
2026-09-30 | P02 | Example: Site supervisor |  | 41 |  | 90 | 3690
2026-09-30 | P02 | Example: Technician |  | 128 |  | 50 | 6400
2026-09-30 | P02 | Example: Labourer |  | 133 |  | 30 | 3990
2026-09-30 | P04 | Example: Project manager |  | 14 |  | 150 | 2100
2026-09-30 | P04 | Example: Site supervisor |  | 44 |  | 90 | 3960
2026-09-30 | P04 | Example: Technician |  | 139 |  | 50 | 6950
2026-09-30 | P04 | Example: Labourer |  | 144 |  | 30 | 4320
2026-10-31 | P01 | Example: Project manager |  | 33 |  | 150 | 4950
2026-10-31 | P01 | Example: Site supervisor |  | 105 |  | 90 | 9450
2026-10-31 | P01 | Example: Technician |  | 328 |  | 50 | 16400
2026-10-31 | P01 | Example: Labourer |  | 342 |  | 30 | 10260
2026-10-31 | P02 | Example: Project manager |  | 13 |  | 150 | 1950
2026-10-31 | P02 | Example: Site supervisor |  | 41 |  | 90 | 3690
2026-10-31 | P02 | Example: Technician |  | 128 |  | 50 | 6400
2026-10-31 | P02 | Example: Labourer |  | 133 |  | 30 | 3990
2026-10-31 | P04 | Example: Project manager |  | 14 |  | 150 | 2100
2026-10-31 | P04 | Example: Site supervisor |  | 44 |  | 90 | 3960
2026-10-31 | P04 | Example: Technician |  | 139 |  | 50 | 6950
2026-10-31 | P04 | Example: Labourer |  | 144 |  | 30 | 4320
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact

## Other costs
Materials, subcontractors and other direct costs
Axcell Financial Consulting · Project Costing & Profitability
Amounts in Your currency, excluding recoverable VAT. One row per invoice or cost. Pick the project ID and category from the lists.
Total logged |  |  |  | 764000
Direct cost log (labour goes on the Labour sheet)
Date | Project ID | Category | Supplier / description | Amount | Reference (optional)
2026-01-15 | P03 | Materials | Example Supplier A (Example) | 13700
2026-01-15 | P03 | Subcontractors | Example Subcontractor X (Example) | 10000
2026-01-15 | P03 | Other | Equipment hire (Example) | 7000
2026-03-15 | P03 | Materials | Example Supplier B (Example) | 13700
2026-03-15 | P03 | Subcontractors | Example Subcontractor Y (Example) | 10000
2026-05-15 | P03 | Materials | Example Supplier C (Example) | 13600
2026-05-15 | P03 | Subcontractors | Example Subcontractor X (Example) | 10000
2026-06-15 | P01 | Materials | Example Supplier A (Example) | 100000
2026-06-15 | P01 | Subcontractors | Example Subcontractor X (Example) | 50000
2026-06-15 | P01 | Other | Equipment hire (Example) | 8300
2026-07-15 | P01 | Materials | Example Supplier B (Example) | 100000
2026-07-15 | P01 | Subcontractors | Example Subcontractor Y (Example) | 50000
2026-07-15 | P01 | Other | Permits and site costs (Example) | 8300
2026-08-15 | P01 | Materials | Example Supplier C (Example) | 100000
2026-08-15 | P01 | Subcontractors | Example Subcontractor X (Example) | 50000
2026-08-15 | P01 | Other | Transport (Example) | 8400
2026-08-15 | P04 | Materials | Example Supplier A (Example) | 23300
2026-08-15 | P04 | Subcontractors | Example Subcontractor X (Example) | 11000
2026-08-15 | P04 | Other | Equipment hire (Example) | 5000
2026-09-15 | P02 | Materials | Example Supplier A (Example) | 44000
2026-09-15 | P02 | Subcontractors | Example Subcontractor X (Example) | 10000
2026-09-15 | P02 | Other | Equipment hire (Example) | 5000
2026-09-15 | P04 | Materials | Example Supplier B (Example) | 23300
2026-09-15 | P04 | Subcontractors | Example Subcontractor Y (Example) | 11000
2026-10-15 | P02 | Materials | Example Supplier B (Example) | 44000
2026-10-15 | P04 | Materials | Example Supplier C (Example) | 23400
2026-10-15 | P04 | Subcontractors | Example Subcontractor X (Example) | 11000
axcellservice.com · Free template · Book a free 30-minute consultation: axcellservice.com/contact